Outdoor Learning Symposium Timeline Suggestions

12 Months (September – November)

- Set the date and venue to be announced at the current symposium

  - Historically symposium has been held in late September to early November. Location needs to have:

    - 1 large auditorium for 200+ people

    - 1 large space for exhibits (15+), EEA store, and OLS Recycle Store

    - 1 large space for lunch

    - Registration space (Wi-Fi is a plus)

    - At least 6 classrooms (3 long sessions and 3 short sessions/technology is a plus)

    - Saturday workshop space

    - Ample parking

    - Access to outdoor areas

    - Recycling?  If not, Green Team can provide bins.

11 months (November – December)

- Debrief council meeting/review evaluations (Historically has been a holiday potluck)

- Submit final report to EEA BOD

- Decide on symposium theme/discuss possible presenters

- Proposed budget submitted to EEA BOD (can be revised, if needed)

    - Budget will determine if presenters and working committee members can attend for free or discounted price.  Do working committee members get free exhibitor space?

- Obtain event sponsors and/or grants

10 – 7 months (January – May)

- Secure presenters by having them complete “Presenter Form,” including Saturday workshop

  - Hands-on sessions that utilize the outdoors are a plus, as are make ‘n takes (creation, utilization, and maintenance)

    - Morning sessions—3 long and 6 short

    - Afternoon sessions—2 long and 6 short

  - Correlated to CCGPS

- Keynote/opening speaker?

8 - 7 months (April – Beginning of May)

- Arrange food (Friday-breakfast, lunch, snack and Saturday-breakfast, lunch, snack)

- Create electronic registration brochure, which includes prices and program

- Submit information to the EEA webmaster to create online registration form

    - Include Q & A Form and list of area hotels with block of rooms reserved

- Submit information to EEA PR/Marketing coordinator to begin promotion

- PR push during teachers’ post-planning (early-bird discount)

- Advertise to potential exhibitors and vendors to register for space

- Information provided to EEA Store Chairperson, including theme in the event there is a need to order merchandise

- Submit PLU request for approval

- Donations for Teacher Recycle Store

- Donations for Resource Table and/or goodie bags

- Donations for Door prizes

- Donations for scavenger hunt prizes

- Donations for carpool prizes

- Update Annual COOL Awards and submit to EEA webmaster for placement on website and the creation of an online submission form (check with COOL Outreach Committee)

3 - 2 months (August – September)

- PR for Annual Outdoor Learning Awards

- PR push during teachers’ pre-planning (last week of July – first week of August)

- Submission of presenters’ handouts for online proceedings

- Finalize program and presenter room assignments

- Finalize presenters’ AV needs

- PLU request forms emailed to participants

- Committee meeting (end of August)

1 month (September)

- Final walk-through of venue with committee

  - How many tables are needed?

  - How many recycle bins?

  - Other onsite logistics

- Create signage

- Create moderator packets

- Create exhibitors’ evaluation

- Sign-up volunteers (set-up, clean-up, moderators, placement of signs, registration, Teacher Recycle Store, Resource Table, EEA Store, exhibits, recycling, AV, photographer(s), door prizes, awards’ presenter, Saturday on-site, Social Media (Twit during the event)

- Create exhibitor scavenger hunt and obtain prizes for completed forms

- Plaques ordered for COOL awards and check requested from EEA treasurer for monetary award

- Committee meeting (September)

1 week

- Finalize food for Friday and Saturday

- Finalize Exhibits/Vendors list (request additional tables/tablecloths, as needed)

- Finalize AV/technology requests

- Finalize nametags, registration packets, and door prize tickets

- Change box for Teacher Recycle Store

- Secure door prizes, scavenger hunt, and carpool prizes

- Create welcome and COOL awards PowerPoint

- Press release sent out

Day Before

- Set up registration area

  - Tables, change box, name tags, registration packets, Wi-Fi for on-site registrations, signage, PLU sign-in

- Presenters/Moderator check-in area with necessary forms and moderator packets drop-off box

- Set-up EEA Store

- Set-up Teaching Recycle Store

- Set-up Exhibit/Vendor Area

- Set up Resource Tables(s) and/or stuff goodie bags

- Place room schedules and other signage in appropriate locations

- Set-up food area

- AV needs and rooms set-up

- Podium decoration for “Welcome/Opening Announcements and COOL Awards”

- Table centerpieces

- Set-up recycle bins, if needed

Week After

- Online symposium evaluation emailed to participants

- Evaluations in moderator packets and exhibitors disaggregated

- Thank you letters sent to sponsors and presenters

- Press release sent out

- Online proceedings submitted to EEA webmaster

- Photographs shared

Sub-Committees

- Program

- Registration

- PR

- Food/Local arrangements (including décor for tables and podium)

- Green Team/Green Exhibit Contest

- Door prizes

- Resources (swag bags&/or pickup table)

- AV/Technology

- Photo Contest

- Teacher Recycle Store

- EEA Store

- Online Session Proceedings

- Website

- Notetaker

- Thank you’s

- Photographer/blogger

- Exhibits/Vendors (includes creating exhibitor scavenger hunt and EEA Banners)

- Signage

- Moderators/Evaluations

- Fundraising

- OL Awards

- Proclamation